## Report Setup
Product GA Readiness — Report Setup
Every project-specific label used by the static HTML begins here. Do not hardcode these values in the template.
Key | Value | Guidance | Calculated dashboard checks
Report ID | contoso-product-ga-readiness | Workbook-owned value used by the deterministic ReportKit adapter. | Days to target
Report Title | Contoso Product GA Readiness | Workbook-owned value used by the deterministic ReportKit adapter. | Confirmed blockers
Subtitle | Management view of product, platform, service, launch content, and customer readiness | Workbook-owned value used by the deterministic ReportKit adapter. | Readiness gates
Product Name | Contoso Secure SDK | Workbook-owned value used by the deterministic ReportKit adapter. | Owners missing
Primary GA Target | Contoso Secure SDK | Workbook-owned value used by the deterministic ReportKit adapter. | Refresh cadence | Daily
GA Target Label | October 30, 2026 | Workbook-owned value used by the deterministic ReportKit adapter.
GA Target Date | 2026-10-30 | Workbook-owned value used by the deterministic ReportKit adapter.
Data As Of | 2026-10-20 | Workbook-owned value used by the deterministic ReportKit adapter.
Generated At | 2026-10-20 18:00 UTC | Workbook-owned value used by the deterministic ReportKit adapter.
Classification | Public sample | Workbook-owned value used by the deterministic ReportKit adapter.
Overall Status | At Risk | Workbook-owned value used by the deterministic ReportKit adapter.
Overall Status Label | GA is AT RISK | Workbook-owned value used by the deterministic ReportKit adapter.
Overall Status Summary | Product engineering is on track, but platform certification and production rollout must complete before approval. | Workbook-owned value used by the deterministic ReportKit adapter.
Decision Question | Can Contoso Secure SDK proceed to general availability on October 30, 2026? | Workbook-owned value used by the deterministic ReportKit adapter.
Refresh Cadence | Daily | Workbook-owned value used by the deterministic ReportKit adapter.
Report Period Start | 2026-10-20 | Workbook-owned value used by the deterministic ReportKit adapter.
Report Period End | 2026-10-30 | Workbook-owned value used by the deterministic ReportKit adapter.
Template ID | microsoft/product-ga-readiness | Workbook-owned value used by the deterministic ReportKit adapter.
Template Version | 1.0.0 | Workbook-owned value used by the deterministic ReportKit adapter.
Primary Color | #1557B0 | Workbook-owned value used by the deterministic ReportKit adapter.

## Readiness Gates
Product GA Readiness — Drone View Gates
One row becomes one executive tile. Keep the gate list short, mutually distinct, and decision-oriented.
Total gates |  | Ready / on track |  | GA blockers
Gate ID | Gate Name | Status | Status Label | Value | Unit | Summary | Owner | Target Date | Blocks GA | Display Order
product-engineering | Product engineering | On Track | ON TRACK | 3 of 3 |  | Core SDK work is complete or on track for the target date. | Contoso SDK Team | 2026-10-30 | No | 1
platform-readiness | Platform readiness | At Risk | AT RISK | 1 of 2 |  | One required secure runtime still needs certification. | Contoso Platform Team | 2026-10-27 | Yes | 2
service-readiness | Dependent service readiness | At Risk | AT RISK | Canary passed |  | The production rollout is not complete. | Contoso Service Team | 2026-10-28 | Yes | 3
documentation | Documentation | Update Required | UPDATE | Draft ready |  | Final approval and publication evidence are required. | Contoso Content Team | 2026-10-29 | No | 4
release-notes | Release notes | Update Required | UPDATE | In review |  | Engineering approval is still pending. | Contoso Release Team | 2026-10-29 | No | 5
announcement | Launch announcement | In Progress | IN PROGRESS | Scheduled |  | Final messaging and channel confirmation remain open. | Contoso Communications | 2026-10-30 | No | 6

## Milestones
Product GA Readiness — Milestones
Track completed, current, and future delivery points. Progress and status are separate: status is the management signal; progress is supporting context.
Total milestones |  | Complete |  | Open |  | Refresh | Daily
Milestone ID | Milestone | Workstream | Milestone Type | Status | Progress % | Owner | Target Date | Completed Date | Dependency | GA Impact | Current Evidence | Next Action | Display Order
milestone-1 | Core dependency released | Product engineering | Release | Complete | 100% | Contoso Identity Team | 2026-10-15 | 2026-10-15 |  | Released dependency | The dependency package is available for consumption. | Maintain release availability. | 1
milestone-2 | SDK integration complete | Product engineering | Integration | On Track | 85% | Contoso SDK Team | 2026-10-24 |  | Core dependency released | Supports primary GA | Integration tests are passing. | Complete release sign-off. | 2
milestone-3 | Secure runtime certification | Platform readiness | Certification | Blocked | 65% | Contoso Platform Team | 2026-10-27 |  | Certification lab capacity | Confirmed GA blocker | The final certification suite has not completed. | Complete certification and publish evidence. | 3
milestone-4 | Production service rollout | Dependent service readiness | Deployment | At Risk | 75% | Contoso Service Team | 2026-10-28 |  | Regional deployment approval | Confirmed GA blocker | Canary validation passed; production rollout is pending. | Deploy globally and validate telemetry. | 4
milestone-5 | GA documentation approved | Launch readiness | Documentation | Pending Review | 70% | Contoso Content Team | 2026-10-29 |  | Engineering review | Launch readiness | Draft documentation is under review. | Obtain final approval and publish. | 5
milestone-6 | Release notes approved | Launch readiness | Release notes | In Progress | 60% | Contoso Release Team | 2026-10-29 |  | Release sign-off | Launch readiness | Release notes have entered review. | Complete engineering approval. | 6
milestone-7 | Announcement scheduled | Launch readiness | Announcement | In Progress | 50% | Contoso Communications | 2026-10-30 |  | Messaging approval | Launch readiness | A draft announcement and channel plan exist. | Confirm approvers and publication time. | 7
milestone-8 | Post-GA adoption checkpoint | Customer adoption | Adoption | Not Started | 0% | Contoso Customer Success | 2026-11-13 |  | GA publication | Follow-on adoption | The checkpoint is planned after GA. | Confirm participating customers. | 8

## Decisions & Support
Product GA Readiness — Decisions & Support
Track the work that needs a management decision, commitment, escalation, or cross-team support. Use Blocks GA=Yes only for the current primary GA decision.
Open requests |  | Blocked |  | Confirmed GA blockers |  | Refresh | Daily
Request ID | Type | Decision or Support Needed | Status | Owner | Needed From | Due Date | Blocks GA | Outcome Needed | Current Context | Next Step | Scope or Related Record | Display Order
request-1 | Decision | Approve additional certification capacity | Pending Review | Contoso Program Team | Contoso Platform Leadership | 2026-10-22 | Yes | Unblock secure runtime certification | Capacity is the remaining constraint. | Confirm the additional test window. | secure-runtime | 1
request-2 | Support | Confirm global rollout window | In Progress | Contoso Service Team | Contoso Operations | 2026-10-23 | Yes | Commit the production deployment schedule | Canary evidence is available. | Publish the approved rollout schedule. | production-rollout | 2
request-3 | Decision | Approve GA documentation | Pending Review | Contoso Content Team | Contoso Product Leadership | 2026-10-27 | No | Authorize publication | The draft is complete. | Record approval and publication date. | ga-documentation | 3
request-4 | Action | Approve release notes | In Progress | Contoso Release Team | Contoso Engineering | 2026-10-27 | No | Authorize release-note publication | Technical review is underway. | Complete review comments. | release-notes | 4
request-5 | Support | Confirm announcement channel | Not Started | Contoso Communications | Contoso Marketing | 2026-10-28 | No | Finalize the launch channel | Two channels are under consideration. | Select the launch channel. | announcement | 5
request-6 | Decision | Confirm support escalation coverage | In Progress | Contoso Support Team | Contoso Operations | 2026-10-28 | No | Confirm launch-day support coverage | Primary responders are identified. | Publish the escalation roster. | support-readiness | 6
request-7 | Action | Schedule the post-GA review | Not Started | Contoso Program Team | Contoso Product Team | 2026-10-30 | No | Create the follow-up governance checkpoint | The review window is reserved. | Send the review invitation. | post-ga-review | 7

## Audience Adoption
Product GA Readiness — Audience & Client Adoption
Separate the primary product decision from adoption progress. A blocked adopter does not block product GA unless Blocks GA is explicitly set to Yes.
Tracked audiences |  | Complete |  | In progress / at risk |  | Refresh | Daily
Audience ID | Audience or Client | Type | Status | Adoption Stage | Progress % | Owner | Target Date | Blocks GA | Current Evidence | Next Action | Display Order
audience-1 | Contoso Finance | Internal customer | Complete | Production validated | 100% | Contoso Customer Success | 2026-10-18 | No | Production validation is complete. | Monitor through GA. | 1
audience-2 | Contoso Commerce | Internal customer | On Track | Pilot | 80% | Contoso Customer Success | 2026-10-25 | No | Pilot traffic is healthy. | Complete production sign-off. | 2
audience-3 | Contoso Analytics | Internal customer | In Progress | Integration | 60% | Contoso Adoption Team | 2026-10-30 | No | Integration tests are running. | Close remaining test cases. | 3
audience-4 | Fabrikam Services | Design partner | At Risk | Pilot | 45% | Contoso Partner Team | 2026-11-06 | No | A compatibility issue remains open. | Resolve the compatibility issue. | 4
audience-5 | Northwind Platform | Design partner | Blocked | Planning | 20% | Contoso Partner Team | 2026-11-13 | No | The partner depends on secure runtime certification. | Resume after certification completes. | 5
audience-6 | Public developer audience | External audience | Not Started | Announcement | 0% | Contoso Communications | 2026-10-30 | No | Publication is scheduled for GA day. | Finalize the announcement package. | 6

## Readiness Details
Product GA Readiness — Detailed Records
This is the authoritative drill-down: every row must show an owner, status, GA impact, evidence, and next action.
Total records |  | Confirmed blockers |  | Missing owners |  | Refresh | Daily
Record ID | Workstream ID | Workstream | Item | Status | Priority | Owner | Accountable Owner | Target Date | Blocks GA | GA Impact | Current State or Evidence | Next Action | Evidence State | Release Scope | Source Reference | Display Order
record-1 | primary-release-path | Product engineering | Core dependency | Complete | High | Contoso Identity Team | Contoso Engineering Leadership | 2026-10-15 | No | Released dependency | The dependency package is available for product consumption. | Maintain release availability. | Verified | Current GA | Release record | 1
record-2 | primary-release-path | Product engineering | SDK integration | On Track | High | Contoso SDK Team | Contoso Product Leadership | 2026-10-24 | No | Supports primary GA | Integration tests are passing. | Complete release sign-off. | Partial | Current GA | Integration review | 2
record-3 | primary-release-path | Product engineering | Contoso Secure SDK | On Track | Critical | Contoso Product Team | Contoso Product Leadership | 2026-10-30 | No | Primary GA target | Packaging and validation remain on track. | Publish the GA package after approval. | Partial | Current GA | GA review | 3
record-4 | product-context | Product context | Contoso Policy Library | Complete | Medium | Contoso Policy Team | Contoso Engineering Leadership | 2026-10-15 | No | Supporting component | The supporting library is released. | Maintain compatibility. | Verified | Current GA | Release record | 1
record-5 | platform-readiness | Platform readiness | Standard runtime | Ready | High | Contoso Platform Team | Contoso Platform Leadership | 2026-10-30 | No | Supported platform ready | Validation is complete on the standard runtime. | Maintain readiness through GA. | Verified | Current GA | Certification report | 1
record-6 | platform-readiness | Platform readiness | Secure runtime | Blocked | Critical | Contoso Platform Team | Contoso Platform Leadership | 2026-10-27 | Yes | Confirmed GA blocker | The final certification suite has not completed. | Complete certification and publish evidence. | Partial | Current GA | Certification tracker | 2
record-7 | service-readiness | Dependent service readiness | Production deployment service | At Risk | Critical | Contoso Service Team | Contoso Operations Leadership | 2026-10-28 | Yes | Confirmed GA blocker | Canary validation passed; production rollout is pending. | Deploy globally and validate telemetry. | Submitted | Current GA | Deployment dashboard | 1
record-8 | launch-readiness | Launch readiness | GA documentation | Update Required | High | Contoso Content Team | Contoso Product Leadership | 2026-10-29 | No | Launch readiness gap | Final approval and publication evidence are missing. | Obtain approval and publish. | Partial | Current GA | Documentation review | 1
record-9 | launch-readiness | Launch readiness | Release notes | Update Required | High | Contoso Release Team | Contoso Engineering Leadership | 2026-10-29 | No | Launch readiness gap | Engineering approval is pending. | Complete approval and publish. | Partial | Current GA | Release review | 2
record-10 | launch-readiness | Launch readiness | Launch announcement | In Progress | Medium | Contoso Communications | Contoso Product Leadership | 2026-10-30 | No | Launch readiness gap | Draft messaging and a channel plan exist. | Confirm approvers and publication time. | Partial | Current GA | Launch plan | 3

## Instructions
Product GA Readiness — Authoring Guide
Use this workbook as the source contract paired with the microsoft/product-ga-readiness ReportKit template.
Step | Where | Rule | Excel Status | Canonical Status | Meaning
1. Set report identity | Report Setup | Update every project-specific value. The HTML title, subtitle, target, dates, classification, decision text, and cadence come from this table. | Complete / Ready | healthy | Finished and verified.
2. Maintain the Drone view | Readiness Gates | Use 4–8 decision gates. Each gate needs a short status label, current value, owner, target date, and one-sentence summary. | On Track | healthy | Expected to meet the target with no known GA-blocking issue.
3. Track delivery milestones | Milestones | Use one row for every meaningful release, integration, platform, announcement, or future-adoption milestone. Enter progress from 0% to 100%, an owner, dependency, evidence, and next action. | In Progress | in-progress | Work has started; no stronger conclusion has been established.
4. Track decisions and support | Decisions & Support | Use this sheet for decisions, commitments, escalations, and cross-team support. Needed From identifies the person or organization that must respond. | At Risk | critical | A material risk threatens the target; explain whether it is a confirmed blocker.
5. Track adoption | Audience Adoption | Use this sheet for target audiences, partners, and clients. Track stage and progress without automatically treating partner delay as a primary GA blocker. | Blocked | blocked | Progress cannot continue without resolving a dependency or decision.
6. Maintain readiness details | Readiness Details | Create one stable row per product, platform, service, or launch deliverable. Owners are mandatory; use Unassigned explicitly when needed. | Update Required | warning | Evidence or owner confirmation is missing.
7. Classify blockers | All tracking sheets | Set Blocks GA=Yes only for a confirmed blocker to the primary GA decision. Avoid counting the same blocker twice; use Scope or Related Record to link a support request to the authoritative readiness row. | Pending Review | pending-review | Work is ready for a named approval or review.
8. Keep the verdict consistent | Report Setup | Overall Status Label and Summary must agree with the rows marked Blocks GA=Yes. Do not call the overall program on track when a confirmed blocker remains. | Not Started | not-started | No implementation evidence is available.
9. Refresh daily | All sheets | Update Data As Of, evidence, owners, statuses, progress, target dates, and next actions once per business day. Hourly refresh is not required. | Unknown | unknown | Status cannot be verified from the current source.
10. Preserve stable IDs | All tracking sheets | Never reuse an ID for another concept. IDs drive grouping, diffing, and reproducible HTML output. | N/A | not-applicable | The gate does not apply to this product.
11. Build deterministically | Report Setup | Generated At is an explicit input. The adapter must not inject the current time or make network calls.